IMO ASSEMBLY 26th session  18 January 2010

Resolution A.1018

ANNEX

TIME FRAME AND SCHEDULE OF ACTIVITIES

TO INSTITUTIONALIZE THE IMO MEMBER STATE AUDIT SCHEME

| IMO Body | Timing | Action |
| --- | --- | --- |
| MSC and MEPC | First half of 2010 | Consider how to make the Code for the implementation of mandatory IMO instruments mandatory, including provisions for auditing |
| MSC and MEPC | Second half of 2010 | Identify mandatory IMO instruments through which the Code and auditing should be made mandatory |
| Council | End 2010 | Establish Joint Working Group (JWG) of MSC, MEPC, FAL and TCC to review the Framework and Procedures for the Scheme |
| MSC and MEPC | 2011 and 2012 | Develop provisions to make the Code mandatory through the identified mandatory IMO instruments |
| Council | Second half of 2011 | Approve a progress report for submission to A 27 |
| Assembly 27 | November 2011 | Receive a progress report and decide as appropriate |
| JWG | 2011 and 2012 | Review the Framework and Procedures for the Scheme |
| JWG | 2013 | Finalize the Framework and Procedures, taking into account the finished product of the Code and the related amendments to mandatory IMO instruments |
| Council | First half of 2013 | Approve the Framework and Procedures for the Scheme, for submission to A 28 for adoption |
| Committees | 2013 | Adopt amendments to the mandatory IMO instruments concerned for entry into force on 1 January 2015 |
| Assembly 28 | November 2013 | Adopt resolution on the Framework and Procedures for the Scheme and amendments to those mandatory instruments under the purview of the Assembly |
| Council, Committees and Secretariat | 2014 | Preparatory work for the commencement of an institutionalized audit scheme |

I:\ASSEMBLY\26\RES\1018.doc